|  |  |
| --- | --- |
| logo_saludmesoam.png | logo-del-BID.jpg |

**División de Protección Social y Salud, SCL/SPH**  
**Iniciativa Salud Mesoamérica 2015, SM2015**  
**Conclusiones de la reunión realizada el: 29 de Marzo de 2014**  
  
**Operación:** BL-G1001  
**Tipo de Reunión:** Seguimiento Mensual de la Ejecución  
**Participantes:** Rafael Soares, Ferdinando Regalia, Emma Iriarte


  

**AVANCE FISICO Y FINANCIERO**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **¿Cuándo fue la última vez que actualizó los datos?** | **Avances Fisicos Planificados (Meta Ejecución)** | **Avances Físicos Reales (Avance en la ejecución real)** | **Avances Financieros Planificados (Ejecución financiera planificados)** | **Avances Financieros Actuales (Ejecución financiera real)** | **Monto Desembolsado** |
| 7 de Marzo de 2014 | 83.0% | 77.0% | 75.0% | 64.0% | 500000.0 |

**Gráficos del Tablero de Control**



**ALERTAS TEMPRANAS Y ESTADO DE LOS HITOS**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Indicador de Pago** | **Hito** | **Trimestre** | **Audiencia** | **Estado Actual** | **Alerta/Notas** | **Recomendación** | **Acuerdo** |
| Health facilities that have implemented Quality of Care job aid tools for reproductive health | Job Aid tools to improve Quality of Care are reviewed, developed, translated and distributed | 2013Q2 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have permanent availability of all 5 types of modern family planning methods  (injectable, barrier, oral, IUD, permanent) according to the norms | Equipment permanent availability of all 5 types of modern family planning methods from UNFPA procured and Regional IUD Training conducted | 2013Q2 | Pais, BID, Donantes | En proceso |  |  |  |
| Norms for improving the quality of reproductive and child health and nutrition services and for the establishment of a community platform of services adopted | Nutrition, Community Platform and SRH Health norms reviewed by URC and approved by MOH | 2013Q2 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities with a mechanism in place for carrying out patient satisfaction surveys | Final format for Patient Satisfaction surveys printed (with assistance from URC) and distributed | 2013Q2 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have implemented Quality of Care job aid tools for reproductive health | Service providers trained on the use of Job aid tools, and Quality Innovation Fund Evaluation Performed | 2013Q3 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have permanent availability of all 5 types of modern family planning methods  (injectable, barrier, oral, IUD, permanent) according to the norms | Tubal Ligation workshop conducted, manuals distributed and Quality Innovation Fund evaluated | 2013Q3 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have sexual and reproductive health (SRH) educational materials specifically targeted at adolescents | Sexual and reproductive health (SRH) educational materials specifically targeted at adolescents distributed and monitored and Quality Innovation Fund Evaluation Performed | 2013Q3 | Pais, BID, Donantes | En proceso |  |  |  |
| Norms for improving the quality of reproductive and child health and nutrition services and for the establishment of a community platform of services adopted | Nutrition, Community Platform and SRH Health norms shared with IDB for revision | 2013Q3 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have implemented Quality of Care job aid tools for reproductive health | Monitoring of Quality of Care job aid tools for reproductive health completed through Quality Innovation Fund mechanism | 2013Q4 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have sexual and reproductive health (SRH) educational materials specifically targeted at adolescents | Monitoring of sexual and reproductive health (SRH) educational materials specifically targeted at adolescents monitoring completed through Quality Innovation Fund mechanism | 2013Q4 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have the necessary inputs for providing emergency obstetric and neonatal care according to the norms | Monitoring of inputs for providing emergency obstetric and neonatal care Monitoring completed for the Quality Innovation Fund mechanism | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have the necessary inputs for providing pre- and post natal care according to the norms | Monitoring of inputs for providing pre- and post natal care Monitoring completed through the Quality Innovation Fund mechanism | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have the necessary inputs to provide child health care according to the norms | Stock Registry for child health care updated by health facilities | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have implemented Quality of Care job aid tools for reproductive health | Quality of Care job aid tools for reproductive health monitoring completed for Quality Innovation Fund | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that can submit and receive data from the Belize Health Information System (BHIS) | 6 Health Facility BHIS reports submitted | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have permanent availability of all 5 types of modern family planning methods  (injectable, barrier, oral, IUD, permanent) according to the norms | Monitoring of permanent availability of all 5 types of modern family planning methods monitoring completed through the Quality Innovation Fund mechanism | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities that have sexual and reproductive health (SRH) educational materials specifically targeted at adolescents | Monitoring of sexual and reproductive health (SRH) educational materials specifically targeted at adolescents monitoring completed through Quality Innovation Fund mechanism | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Community health workers (CHW) trained in the community platform | Community Health Workers (CHWs) training by topic completed according to the manual | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| District Health Education and Community Participation Bureau (HECOPAB) Officers that are currently monitoring the CHWs | Monitoring of District Health Education and Community Participation Bureau (HECOPAB) Officers that are currently monitoring the Community Health Workers (CHWs) completed through the Quality Innovation Fund mechanism | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |
| Health facilities with a mechanism in place for carrying out patient satisfaction surveys | Monitoring of Health facilities with a mechanism in place for carrying out patient satisfaction surveys completed through the Quality Innovation Fund mechanism | 2014Q5 | Pais, BID, Donantes | En proceso |  |  |  |